## Sheet1
Great | [8 empty] | 2013-01-09 | Senior Project Doc. Workshop: 2nd Eng. Clinic | [5 empty] | 2013-01-28 | Full paper submission (ISPC)
Beer | [8 empty] | 2013-01-23 | The 4th Senior Project mini Poster Exhibition 2013
Ta | [8 empty] | 2013-01-30 | The 3rd Senior Project Conference 2013
Date |  | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-05 | 2013-01-06 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-12 | 2013-01-13 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-19 | 2013-01-20 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-26 | 2013-01-27 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31
Version 0.1
Function | 1. Physics of character movement regarding oblique terrains | bar: 2013-01-02 to 2013-01-06
2. Fundamental lighting in ferest map | bar: 2013-01-02 to 2013-01-06
3. Scene set up in 2D map and transform to 3D | bar: 2013-01-02 to 2013-01-06
4. Action of main character
4.1 Walking | bar: 2013-01-02 to 2013-01-06
4.2 Jumping | bar: 2013-01-02 to 2013-01-06
Scene | 1. Two Scene | bar: 2013-01-03 to 2013-01-09
1.1 Welcome Inteface | bar: 2013-01-03 to 2013-01-09
1.1.a Button, GUIs | bar: 2013-01-03 to 2013-01-09
1.1.b GUISkin (research) | bar: 2013-01-03 to 2013-01-09
Submit
| 1.2 Sample Scene | 2013-01-16: Complete
| 1.2.a size document (unit) | 2013-01-16: Poster
| 1.2.b concept plan and screenshots | 2013-01-16: and
| 1.2.c Models and Texture | 2013-01-16: Abstract
1.2.d Folder organization | bar: 2013-01-03 to 2013-01-09; 2013-01-16
Document | 2. Document
2.1 Design
2.1.a Interface
2.1.b Terrain (concept/sketch)
2.2 API (Obj. list/Scrips)
2.2.a Input/Output
2.2.b description
2.2.c chronological / MapScript
SE testng | 3. mini-Evaluation | bar: 2013-01-03 to 2013-01-09
3.1 Survey form (20 persons) | bar: 2013-01-03 to 2013-01-09
4. Test Criteria | bar: 2013-01-03 to 2013-01-09
5. Web Form
5.1 request Module-set piority/cost/price/level of difficult
5.2 request 3D model
5.3 Bug report-(G/Y/R)-Date
5.4 ER design
Version 0.2
Model | 1. Main character
1.1 One monster
1.2 Tree
1.3 Stone
1.4 Grasses
Function | 1. Action
1.1 Physical attack
1.2 magical attack
2. AI for one monster